## DB Validation Report
Database Validation Report — Zuna E-Commerce Application
SkillShikshya QA Batch 10 ¦ Prepared by: Anita Singh ¦ Test Date: 9–10 August 2026
Scope note: Full CRM-side validation was initially blocked by BUG-000 (documented admin credentials admin@admin.com/admin returned "Invalid credentials"). Access was restored on 10 Aug 2026 using alternate credentials (bikesh@vrittechnologies.com) provided by the instructor. Validation below compares data consistency between the customer-facing storefront (zunadesigns.com) and the CRM (crm.zunadesigns.com) admin panel, which is backed by the same database.
ID | Module / Area | Validation Check Performed | Expected Result | Actual Result (Observed) | Status | Related Bug/Obs ID | Notes / Evidence
DB-001 | Orders | Place a test order on customer site (Anita Singh, COD) and verify it appears correctly in CRM Order Details. | Order appears in CRM with matching customer name, amount, and payment method. | PASS — Order AHYPI6 found in CRM: Anita Singh, NRs. 3099.00, Cash on Delivery, Payment Status: Pending, Delivery Status: Pending. Matches the order placed on the customer site. | PASS | — | Confirms customer-site and CRM share a consistent, synced order record.
DB-002 | Orders | Cross-check Payment Status vs Delivery Status logic across the order list for consistency. | An order with Payment Status = Failed should not be able to reach Delivery Status = Delivered. | FAIL — Order ONMMIC shows Payment Status: Failed but Delivery Status: Delivered. A failed payment should not result in a completed delivery. | FAIL | BUG-006 (new) | Logical data-integrity issue between payment and fulfillment status fields; recommend backend validation rule.
DB-003 | Orders | Check for test/junk data present in the live Orders table. | Production order records should contain only genuine customer data. | OBSERVATION — Several orders contain placeholder/test customer names, e.g. “Order Confirmation Dialog Test”, “LOL BRO LIKE AND SUBSCRIBE”, “LOL”. | OBSERVATION | OBS-008 (new) | Indicates test data was not cleaned from the production/shared database before this testing cycle; not a functional defect.
DB-004 | Returns | Verify Return records correctly store which product is being returned. | Each return record should display the associated product name. | FAIL — Both existing return records (0NZ3MR – Pratibha Chaudhary, LAFJ1U – Bibek) show a blank/empty Product column. | FAIL | BUG-007 (new) | Product reference appears to not be saved or not be joined/displayed correctly for return requests.
DB-005 | Returns | Check data quality of Return reason/notes fields. | Reason field should contain a genuine customer-provided reason. | OBSERVATION — One return reason reads “example plalkdjsflkajsdf” (test data); another simply reads “ok”. | OBSERVATION | OBS-008 (new) | Same test-data hygiene issue as DB-003, extends to the Returns table.
DB-006 | Delivery Charges | Verify delivery charge shown at customer-site checkout (Jhamsikhel, Lalitpur — Rs. 0) against CRM-configured delivery zones. | CRM zone configuration should explain the Rs. 0 charge seen at checkout. | VERIFIED — CRM → Delivery Charges shows “Inside Valley” zone (Kathmandu, Lalitpur, Bhaktapur) is configured with Delivery Charge = 0.00 and Free Delivery Above = 0.00. This is intentional configuration, not a defect. | VERIFIED | OBS-007 (resolved) | OBS-007 from the Bug Report is resolved: the Rs. 0 fare is correct, expected behaviour — reclassify from open observation to verified/working-as-configured.
DB-007 | Dashboard / KPIs | Capture CRM Dashboard summary KPIs as a database-level baseline snapshot. | KPI cards should reflect current aggregate data from the database. | PASS — Total Revenue: NRs. 48,026 ¦ Total Orders: 24 ¦ Total Customers: 2,871 ¦ Total Products: 6, captured 10 Aug 2026. | PASS | — | Baseline figures recorded for reference; not independently cross-verified against a raw DB query (no direct DB access provided for this project).
DB-008 | Products / Top Sellers | Verify Top Selling Products list references valid, existing products. | Every row in Top Selling Products should resolve to an existing product record. | FAIL — The #1 ranked item by revenue (13 units sold, NRs. 40,897 — the single highest revenue entry) displays “Product no longer available” instead of a product name. | FAIL | BUG-008 (new) | Orphaned reference: sales/order data points to a product record that has since been deleted, breaking referential integrity and understating catalogue-level reporting accuracy.
DB-009 | Navigation / Site Settings | Access Site Settings → Payment Gateway to verify configuration behind BUG-001 (missing eSewa/Khalti at checkout). | Payment Gateway toggles for eSewa/Khalti should be viewable to confirm root cause. | RESOLVED ON RETRY — Site Settings sidebar item expanded (chevron toggled) but rendered no submenu items (Banners, Payment Gateway, Featured Drops, Community Gallery, etc.) on first attempt. On a subsequent attempt in the same session, the submenu rendered correctly and Payment Gateway settings were successfully viewed, confirming BUG-001's root cause (Khalti = OFF, eSewa = OFF, Fonepay = ON). Not reproducible on further attempts. | Intermittent | BUG-009 (new) | Likely a front-end rendering race condition or slow data fetch for the submenu; not consistently reproducible. Root cause of BUG-001 IS confirmed (see BUG-001 evidence, Fig. 16 — CRM Payment Gateway screenshot).
DB-010 | CRM Access | Re-validate CRM admin login after instructor provided alternate credentials. | Login should succeed with a valid, working credential set. | PASS (with finding) — Login succeeded using bikesh@vrittechnologies.com. The originally documented admin@admin.com/admin credential set (from official project materials) remains invalid — confirmed at both UI and API level. | PASS | BUG-000 (updated) | BUG-000 status updated to Resolved-with-finding: access restored, but project documentation still contains an incorrect admin credential set.
Summary
Total Checks | Pass | Fail | Observation | Intermittent | Verified (resolved)
10 | 3 | 3 | 2 | 1 | 1
New defects/observations raised in this report: BUG-006, BUG-007, BUG-008, BUG-009, OBS-008 — all added to Bug_Report_Zuna.xlsx (consolidated tracking complete).